| Community Goal I: Improve the Built Environment and Intermodal Transit |  |  |  |  |
| --- | --- | --- | --- | --- |
| MAPPS Strategies addressed: Promote increased physical activity; promote active transportation and walking |  |  |  |  |
| MAPPS Criteria | Objective | Key Activities | Timeline | Outcome |
| Access | Objective 1: Create, adopt and apply a city-wide Health Impact Guideline to all built structures within the City by January 2011 |  CPPW Planning Coordinator* will work with City Planning Department and Board of Health to create voluntary Health Impact Assessment guidelines for systematic review of built environment to ensure support for active living  To systematically review all built structures to ensure support for active living |  Complete Assessment Guideline draft by Q3†  Review by Planning and Zoning by Q4  Review by Mayor's Office by Q5  Review by City Council by Q6  Adoption by City Council by Q7 |  Adoption of Health Impact Assessment policy by the Fall River Board of Health and the Planning and Zoning Departments |
| Access | Objective 2: Update and revise the 2004 Open Space Plan to encourage planning for active living |  CPPW Planning Coordinator* will work with the Planning Department to review the current Open Space Plan, develop public input hearings, research and gather relevant information and propose an updated Plan for review by the Mayor's Office. |  Undertake review process by Q4  Schedule public hearings by Q5  Complete draft Plan by Q6  Recommend adoption by Mayor's Office no later than Q7 |  Completion of an updated Open Space Plan that incorporates recommendations designed to ensure active living among City residents |
| Access | Objective 3: Conduct an assessment of current sidewalk conditions on each of the 11 designated walking routes, around all city parks, and on all Safe-Routes-To-School routes. |  CPPW Planning Coordinator* will work with Department of Public Works staff and school and citizen group volunteers to organize and conduct systematic inventory of city sidewalk conditions |  Review process planned by Q3  Groups organized and trained by Q4  Surveys conducted in Q4 and Q6  Surveys results compiled and report supplied to DPW, Planning and City grant writer by Q7 |  Completion of an inventory of walking route sidewalks city-wide and recommendations for improvement will be available by 2012 |
| Access Media | Objective 4: Create a city-wide inter-modal transit system to support pedestrian/bicycle access integrated with new city bus station by June 2012 |  CPPW Planning Coordinator* will Work with Southeast Regional Transit Authority (SRTA) & SRPEDD† on development of new bus station and pedestrian and bicycle access points;  CPPW Planning Coordinator* and the CPPW Media Coordinator will develop a plan to market use of inter-modal transit routes city-wide with employer incentives and create new inter-modal transit maps and route signage for City showing routes and linkage points  CPPW Planning Coordinator * will work with Public Works director to plan and carry out the installation of bicycle racks city-wide |  Meet with SRTA board and director and SRPEDD staff to review plans for new ARRA-funded bus station to be constructed by Q2  Identify access points and route changes by Q3  Route signage installed by Q4  Bus racks and signs purchased and installed by Q5  Work with SRTA and SRPEDD to create transit map by Q4  Bicycle racks installed by Q3  Maps published and distributed by Q5 |  Completion of a city-wide inter-modal route system with linkage points within the city for bicycle racks and with system-wide signage installed to encourage pedestrian-bicycle-bus transit by 2012  Increase bicycle-related ridership by at least 5 times current rate as measured by driver survey reports |
| Access | Objective 5: A minimum of 22 crosswalk signals will be upgraded and at least ten miles of city streets will be striped for bicycle lanes by June 2012 |  CPPW Planning Coordinator* to work with city traffic engineer to plan upgrades of pedestrian crosswalks, bicycle lane striping, and traffic complete streets for all newly planned construction  Existing Traffic Department funds will be used to upgrade a minimum of 22 crosswalk signals to countdown style and stripe at least 10 miles of streets for bicycle access |  Review of existing and new plans for street improvement completed by Q3  Plan, layout and stripe Eastern Ave, Plymouth Ave and Bay Street for bicycle access by Q4  Secure City funding, purchase and install 9 crosswalk signals by Q6  Identify, purchase and install 13 additional crosswalk signals by Q7 |  Completion of bicycle lane striping for ten miles of four-lane and wide two-lane city boulevards and installation of 22 countdown signals six major intersections completed by 2012 |
| Community Goal II: Develop Urban Parks and Pathways and an Advocacy Network |  |  |  |  |
| Strategies addressed: Promote increased physical activity; promote active transportation and walking |  |  |  |  |
| MAPPS Criteria | Objective | Key Activities | Timeline | Outcome |
| Access Media | Objective I: By 2012, over twenty miles of trails through natural wooded areas surrounding the City's water supply will be created to increase access by City residents for recreation. |  CPPW Urban Parks Coordinator* will work with the The Trustees of Reservations and the Watuppa Water Board property manager to create & market a city-funded walking/bicycle trail system in a 516 acre portions of the 14,000 acre Bioreserve newly opened to public use  Work with CPPW Planning Consultant* and SRTA and SRPEDD staff to establish bus weekend route access from downtown |  Complete trail development mapping and layout by Q3  Work with youth conservation corps to solicit volunteer assistance in trail construction through Q4  Develop signage and maps for distribution by Q5  Finalize routing of SRTA buses with bike racks to include six Saturday runs from Q6 to Q8 |  Trail system plans are completed by 2011 and 50% constructed on City Water Board property for use by pedestrians and cyclists by 2012  Weekend bus linkage to Bioreserve is secured by 2012 |
| Access Media | Objective 2: By 2012, promote community use of designated walking routes through an active marketing plan and installation of signage/social support kiosks on each route. |  CPPW Urban Parks Coordinator* will work with the CPPW Media Coordinator* to plan, create and implement a city-wide "Fall River Walks" media campaign to increase use of the City's ten designated walking routes and woodlands trail system  Purchase and install information kiosks on each routes for use by local groups |  11 walking route kiosks installed by Q3  Marketing campaign for existing "Fall River Walks" developed for local radio, television, print and outdoor advertising by Q5  Promotional campaign to increase use of trails begun with local organizations by Q6 |  Develop marketing plan  Install 12 kiosks to support social marketing |
| Access Social Support | Objective 3: Use of existing parks and open spaces will be increased by 200% by engaging local citizens in ownership and involvement with park protection and improvement. |  CPPW Urban Parks Coordinator* to work with Department of Parks and Cemeteries and city grant writer to explore resources to upgrade city parks and open spaces  Coordinator to work with local sports teams to organize voluntary improvement efforts in City's 23 parks using $8,000 annual Putnam Conservation Institute grant funding |  Meet with Board of Parks and Cemeteries to identify current issues with park maintenance and vandalism through Q3  Citizen volunteers organized to work on park improvement over Q3 and Q7  Exploration of grant funding resources for park improvement and applications filed by Q4 |  Citizen involvement in park maintenance and improvement will increase fivefold as measured by counts of volunteer hours and use of existing parks by 200% as measured by Parks Department schedule of use |
| Access Social Support | Objective 4: Develop an advocacy network to support future park and open space development for recreational purposes by 2010. |  CPPW Urban Parks Coordinator* to work with the Trustees of Reservations and the Putnam Conservation Institute to develop an Urban Parks Advocacy Network that will support park planning, development, funding, stewardship and public support |  Work with the Trustees of Reservations and the Putnam Conservation Institute to enlarge Network membership to 100 by Q3  Plan and hold at least 12 bi-monthly meetings of advocates by Q8 and one major conference per year to support Network development |  Urban Parks Network created for park and urban space development to support active living will be in place by the end of 2010  Member involvement will increase to 100 by 2012 |
| Community Goal III: Increase Participation in Youth Recreation and Fitness Challenge |  |  |  |  |
| MAPPS Strategies addressed: Promote increased physical activity; required physical activity in after-school settings; decrease screen time; social support for physical fitness activity |  |  |  |  |
| MAPPS Criteria | Objective | Key Activities | Timeline | Outcome |
| Access Social Support Price | Objective I: Increase physical activity and decrease screen time of youth during summer months by providing 4-hour daily Summer Olympics program at 9 of 13 city parks |  CPPW Fitness Coordinator* to train and supervise summer youth recreation staff to provide program of active play through a Summer Olympics program at 13 city parks that provide free USDA-funded lunches for low-income children  Work with Family Service Association, YMCA and Boys and Girls Club after-school programs to offer HEAT Clubs by providing curricula and staff education |  Youth employees trained and equipped to provide program of active games for over 1,000 youth participants in the USDA lunch program by Q3  Children In Balance HEAT Clubs will become operational at all city after-school programs by Q4 |  Participation in current Summer Olympic program to increase from 100 to 300 by 2012  100% of after-school programs will have CIB-style HEAT Clubs by 2012 |
| Access Social Support Price | Objective 2: Increase participation in successful annual low-cost weight-loss and physical fitness and nutrition education program by providing 1-on1 social support from student nurses |  CPPW Fitness Coordinator* will work with fitness/nutrition consultants build on two successful years to develop/market a city-wide, year-round Fitness Challenge program for adults/teens that uses social support from 90 LPN nursing students to increase participation of 2,000+ city residents in a low-cost, city-funded program  Develop linkages between Challenge and local physicians to verify participation on a prescription basis |  Evaluate first year of supported Fitness Challenge by Q2  Add participation of 30 community college nursing students by Q3 to make over 150 support partners available to participants  Link verified participation in fitness with prescribing physicians |  Increase participation in Fitness Challenge to 2,000 by 1/2011  Increase involvement of nursing students by 30%  Enroll 25 physicians who receive reports of FC participation by patients |
| Access Social Support Price | Objective 3: Increase participation in annual Fitness Challenge by employees in 50 companies and organizations by 200 percent over a 2-year period; enhance community ownership and participation by June 2012 |  CPPW Fitness Coordinator* to work with CPPW Media Coordinator* and the Chamber of Commerce to market the annual community-wide Fitness Challenge to increase participation by employees in small businesses, civic organizations, clubs and sports teams and survey results  Identify an additional 50 worksite-based and family teams to increase participation to 2,000 by 2011  Work with CPPW Cultural Interpreters* to develop specialized marketing materials for non-English-speaking populations to increase involvement in the Challenge |  Plan, develop and implement Fitness Challenge marketing plan among area businesses by Q3  Outreach to 5,000 employees at the Industrial Park by Q4  Outreach to 3,000 City employees by Q4  Outreach to 30 sports clubs and civic organizations by Q4  Prepare marketing materials in 3 languages by Q7 |  Reach 50% of the general adult population and 75% of the workplaces and 100% of clubs and organizations and 20% of bilingual speakers with Fitness Challenge marketing campaign messages by 2012 as measured by UMass Center for Policy Development marketing survey |
|  | Objective 4: Ensure that all Fitness Challenge participants are tracked and linked with support partners throughout both fall Warm-up and winter-spring Challenge; market calendar of events |  CPPW Fitness Coordinator* to develop city-wide system to register and track Fitness Challenge participants and pair them with student nurse support partners  Maintain database and coordinate communication between participants and support partners  Develop HIPPA-compliant fitness participation reporting system and link with participating providers |  Work with current Fitness Challenge staff at CD-REC program to understand and support current registration system by Q2  Develop improved computerized registration and tracking system; work with three area schools of nursing schools to coordinate communication and assignment of students to Challenge participants by Q4  Develop and deploy linkage system with physician practice offices by Q5 |  Design and implement computer-based registration and tracking system for fitness challenge participants, student nurse support partners and physician practices by October 2011. |
| School Goal I: Develop a Sustainable Safe-Routes-to-School System |  |  |  |  |
| MAPPS Strategies addressed: Promote increased physical activity; social support for walking |  |  |  |  |
| MAPPS Criteria | Objective | Key Activities | Timeline | Outcome |
| Access | Objective 1: Assess the "walk-ability" of walking routes to each of the nine elementary schools and determine best routes |  CPPW Safe Routes Coordinator* to work with CPPW Planning Coordinator*, MassRides, the Fall River Police Department and the Department of Public Works to assess potential walking routes to each of the nine elementary schools  Conduct physical walk-ability assessment of each of the planned routes |  Engage school officials, school committee members and PTOs involved in planning and preparation in Q2 for Safe-Routes-to-School pilot launch in Q4 and Q6  Evaluation completed byQ6  Full launch Q7 | 100% of school officials, school committee members and PTOs are involved in the initial planning as measured by meeting minutes |
| Access | Objective 2: Develop computerized master walking route database to assign all students to a safe walking route to school by September 2011 |  CPPW Safe Routes Coordinator* to work with Fall River Police Department and school administration to designate safe routes for groups of children and to designate safe houses along each route; work with Fall River Police to train school crossing guards and parent walking leaders  Prepare for pilot launch  Evaluate  Prepare for full launch |  Walk-ability assessment of planned routes completed by Q3  Student address and GPS coordinates loaded by Q4  Routes published and distributed to parents by Q5  Students assigned by end of Q6  Safe-Routes program launched in fall of Q7  Program evaluated in Q8 |  Pilot program at two schools launched and evaluated by Q4  Full launch by Q7 |
| Access Social Support | Objective 3: Revise the School Wellness Policy to include safe routes definitions and procedures and develop a marketing campaign by 2011 |  CPPW Safe Routes Coordinator* to and load and learn transportation planning software; GPS address points for all children identified  Planning reports tested for use by Q4; students assigned at two pilot schools for implementation in the Fall of 2011  Coordinator to work with CPPW Media Coordinator* to develop marketing campaign |  Designated walking routes assigned to pilot school students by Q4  Crossing guard training completed by Q4  Safe house designation completed for pilot school walking route by Q4  Routes for the remaining 7 designated by Q6  Full program launched by Q7 |  Computerized system of student assignment completed for two pilot schools by Q4 and all schools by Q7  100% of students assigned; Marketing plan completed and in effect |
| Access Media | # Objective 4: Ensure that all routes to school are free of snow and ice during winter months |  CPPW Safe Routes Coordinator* to work with CPPW School Wellness Coordinator* to plan for, approve and roll-out of revised policy to include Safe-Routes language for all schools  Coordinator to work with CPPW Media Coordinator* to develop and implement system-wide a counter-marketing plan to discourage parents from driving students to school |  Safe-Routes-To School policy completed by Q3 for all schools  Marketing plan in place by Q5  Policy announcement sent to parents by Q4  Marketing campaign to run through Q5 and again in Q6 and Q7 |  School policy revised to support active walking  Participation in Safe-Routes to reach 50% of students who are not within the mileage limits for bussing by 2012 as measured in survey |
| Access Social Support | # Objective 5: Increase adolescent physical activity through paid snow-removal employment supported by fines; regulation covering use of snow-removal fines will be passed by City Council |  CPPW Safe Routes Coordinator* to work with City Youth Services coordinator to create youth-run snow shoveling service for indigent and elder residents to ensure that sidewalks are clear of snow through the winter months  Police to mandate increased enforcement of snow removal ordinances  Collected fines directed to Youth Services to pay youth for removal |  Youth Shovel Corps created through Community Development Recreation program in concert with City Council and Public Works Department to create City regulation change by Q4  Program operates in Q5; Evaluate and problem-solve in Q6  Revise program and run again in Q8 |  95% of sidewalks on Safe-Routes-to-School remain free of snow through winter months as measured by student in-school survey  A minimum of 15 students employed by Youth Shovel Corps |
| School Goal II: Develop and Implement the School Wellness Policy |  |  |  |  |
| MAPPS Strategies: Promote healthy food and drink choices, limit unhealthy foods, increase healthy drink availability; increase after-school physical activity |  |  |  |  |
| MAPPS Criteria | Objective | Key Activities | Timeline | Outcome |
| Access | Objective 1: Ensure that menu planning meets fresh fruit and vegetable guidelines under the Massachusetts Farm-to-School program; develop ongoing contract system to ensure supply of fresh produce from local growers |  CPPW School Wellness Coordinator* will work continuously with all levels of school administration, members of the School Committee, parent groups and other CPPW coordinators to revise, update and oversee the implementation of the School Wellness Policy including addition of Safe-Routes-To-School bicycle and pedestrian safety, healthy food and beverage choices, menu planning, after-school physical activity and other related concerns |  Establish a school-wide advisory board to review school wellness policy with school administration by Q3  Prepare educational materials for use in teacher training Q4  Launch year-long wellness policy implementation process in Q5 and Q6  Monitor policy implementation and report on deficits and plan of correction by Q7 |  Menu planning system will be in place by Q4  Contract system to ensure supply of fresh produce will be in place by Q6  A system-wide advisory board will be in place by 2010 to monitor and revise wellness policy for all aspects of health, physical education, nutrition, bicycle and pedestrian safety & after-school physical activity |
| Media Point of Purchase | Objective 2: Reduce the consumption of sugar-based beverages and to promote water and low-fat milk as the drink-of-choice for students |  CPPW School Wellness Coordinator* will work with the CPPW Media Coordinator* to plan and implement a system-wide healthy food & beverage internal media campaign to promote healthier food and beverage choices among students & staff using print, theatre, video and school presentations to carry messages |  Research and plan system-wide healthy food and beverage media campaign within all school buildings and at school events by Q4  Test market and launch campaign for Q5 through Q8 through integration with existing school activities |  A sustainable internal Healthy Food & Beverage campaign will be planned and delivered in 100% of Fall River Schools by 2012 |
| Point of Purchase | Objective 3: Reduce the consumption of sugar-based beverages and to promote water and low-fat milk as the drink-of-choice for students and staff by reviewing existing contracts to ensure that vending contracts are in compliance with all aspects of the system-wide Wellness Policy |  CPPW Food Service Menu/Training Coordinator* will oversee the purchase of all beverages for sale or distribution within the school system to promote healthier choices and to increase the availability of tap water at all school events  Consultant will work with the CPPW School Wellness Coordinator* to revise the Wellness Policy to reflect changes |  Review existing contracts for beverage purchase within the school system by Q3  Re-contract for replacement of sugary beverages by Q4  Develop and conduct healthier choice marketing and counter-advertising campaign by Q4 |  100% of high calorie beverages will be replaced with healthier options including tap water in all school locations and events by 2013  Wellness policy revised |
| Access Point of Purchase | Objective 4: Increase awareness of and rationale for healthier food options in order to encourage students & staff to migrate to these options |  CPPW Food Service Menu/Training Coordinator* will work with the School Food Service Director to conduct menu planning, food ordering and related training to improve the system-wide food service to enable 50% more fresh fruits and vegetables  Institute calorie analysis software program to produce menus with full nutrition info for students and parents  Provide staff training for cafeteria workers and related school personnel |  Develop and renew fresh fruit and vegetable grant by Q2  Renew farm-to-school with local produce providers by Q3  Develop school menus in accord with Mass. School Nutrition Association standards by Q4  Produce school menus with full nutrition information by Q4 Train staff as needed |  Fresh fruit and vegetable content of school menus to increase by 50% in all schools by 2011  100% of school menus to list nutrition information by 2011 |
| Access | Objective 5: Make exercise and nutrition instruction part of the curriculum for after-school programs system-wide |  CPPW Safe Routes Coordinator** will also work with the CPPW School Wellness Coordinator* public school after-school staff and staff at the Boys & Girls Club, the YMCA, and the Family Service Association to incorporate HEAT (Healthy Eating and Active Time) Club activities into after-school and summer programs  Coordinator will work with the CPPW Media Coordinator* to develop internal marketing materials (flyers and posters) | Work with after-school staff to review to determine readiness to expand programming to include HEAT Club activities  Copy and distribute HEAT Club curricula  Set up and run staff training in each agency  Launch programs in conjunction with media campaign | At least 500 children served by three after-school and summer youth programs will be enrolled in daily HEAT Clubs as measured by attendance records |
| Community Goal IV: Increase School/Community Gardens & Farmers' Markets |  |  |  |  |
| MAPPS Strategies: Promote healthy food and drink choices, limit unhealthy foods, increase healthy drink availability; increase after-school physical activity |  |  |  |  |
| MAPPS Criteria | Objective | Key Activities | Timeline | Outcome |
| Access | Objective 1: Offer 100% of elementary school children a nutrition-based gardening experience by engaging them in hands-on learning incorporated into school curricula |  CPPW Community Garden/Market Coordinator* to replicate model school garden at Watson School to all nine elementary schools; develop and share curricular materials that integrate gardening activities with all aspects of the school curriculum  Identify community funding sources for garden construction; link with YMCA Southcoast, Sharing the Harvest – Dartmouth YMCA in developing a regional Community Garden Network |  Plan for the replication of two additional gardens by Q3  Coordinate construction by Q2  Coordinate summer gardening schedule with youth employees  Plan for the replication of the final six school gardens by Q6  Integrate school gardens into curricular materials by Q7 |  School vegetable gardening experiences will be available to 100% of elementary school and learning modules integrated into the school curriculum by 2012 |
| Access Media | Objective 2: To establish a network of at least fifteen gardens throughout the City in concert with organizations |  CPPW Community Garden/Market Coordinator* to support development of the current six community gardens and expand by an additional nine through coordination with the Housing Authority, Neighborhood Associations, youth programs (after-school & summertime) and worksites  CPPW Community Garden/Market Coordinator * to increase participation in community gardening; work with Brix Bounty Farm director to offer education programming throughout the year to increase skills |  Support development of six existing gardens by increasing social support and education to volunteer gardeners by Q2  Begin development of six new gardens by Q3  Provide skill development, grant search and social network development to support new gardens; support development of six more gardens by Q6 |  Create a network of voluntary support and education for an expanded and sustainable community garden infrastructure city-wide with over 1,000 youth and adult participants by 2012 |
| Access | Objective 3: To increase fruit and vegetable consumption and heart-healthy diet esp. to low-income population in concert w/cable tv cooking & nutrition program |  CPPW Community Garden/Market Coordinator * to work with local farmers and the SE Mass. Agricultural Partnership develop mobile fruit & vegetable sales system, targeting housing developments and poor housing locations  Location of EBT machines in housing offices and token system for SNAP purchases  Work with the CPPW Community Market Coordinator* to coordinate with local media campaigns and cable TV cooking show | Contact local farmers, SE MA Agricultural Partnership, and FR Housing Authority to plan "veggie-mobile" system for delivery to 5 HA developments and elder high rises by Q3  Install EBT machines and token system by Q3  Coordinate with cable TV food show | Create a sustainable system of fresh food delivery and purchase for low-income families and elders in all housing developments; link system with local TV food show |
|  | Objective 4: To develop work-site markets and CSA to increase fruit and vegetable availability and lower prices for employees |  CPPW Community Garden/Market Coordinator * to identify potential work-site for in-house markets modeled on Lightolier Co. system and linkages to provide Community Supported Agriculture deliveries to worksites  CPPW Community Garden/Market Coordinator* to coordinate internal company publicity with city-wide marketing campaign |  Research and replicate Lightolier market with five additional worksites by Q4  Replicate five additional worksites by Q7  Promote CSA deliveries to six organizations/worksites by Q4 and six additional ones by Q7 |  Increase availability of fresh fruits and vegetables through markets and CSAs to 1,500 employees at worksite by 2012 |
|  | Objective 5: To increase low-cost healthy options to English and bilingual populations in concert with cable television cooking & nutrition program |  CPPW Community Garden/Market Coordinator* to work with owners/managers to place fruit & vegetable racks in neighborhood markets  CPPW Community Garden/Market Coordinator * to encourage SNAP EBT sales through city-wide media campaign  Coordinate with cable television cooking and weekly nutrition program produced by the high school & community college to increase knowledge of lower cost meal planning and food purchases in local stores |  Survey neighborhood markets to determine interest in voluntary produce rack placement by Q5  Work with store owners to increase EBT produce sales by Q6; coordinate with cable television cooking and nutrition program produced by the high school & community college to increase sales of produce |  Create a sustainable system to increase produce sales in neighborhood markets supported by SNAP EBT sales and coordinated with an ongoing cable TV cooking and nutrition program by 2012 |
| Community Goal V: Make Improvements to the Food Supply & Support Breastfeeding |  |  |  |  |
| MAPPS Strategy: Increase availability of lower prices for healthier food choices among pregnant/parenting mothers; increase social support for breastfeeding |  |  |  |  |
| MAPPS Criteria | Objective | Key Activities | Timeline | Outcome |
| Media Social Support | Objective 1: Increase fruit and vegetable consumption among English and bilingual low-income pregnant and parenting mothers |  CPPW Healthy Food/Dining Coordinator* and CPPW Community Health Interpreters* to work with WIC office to develop and launch Healthy Food & Fitness campaign for pregnant and parenting mothers in English, Portuguese, and Spanish and to provide social support through Early Intervention & WIC; work with neighborhood store owners and larger grocery store managers to promote campaign  Provide social support through community cable TV program |  Work with Early Intervention Program and WIC program to develop Healthy Foods marketing campaign in three languages by Q3  Test market and revise program by Q5  Launch program city-wide by Q6 and evaluate effectiveness by Q7  Revise and re-launch |  Create an effective Healthy Food & Fitness campaign capable of reaching 300 pregnant and parenting mothers in English, Portuguese & Spanish |
| Access Media Price | Objective 2: Work with local food suppliers to increase fruit and vegetable availability to WIC recipients |  CPPW Healthy Food/Dining Coordinator * to work with local markets and produce suppliers to ensure availability of fresh produce and other items on WIC New Food Package lists  Help to resolve delivery issues and keep prices low; develop and coordinate local marketing efforts with supplies  Coordinate with menus for local cable TV cooking show  Increase knowledge base and skill level to increase home meal preparation through cable TV show and educational programs at WIC office |  Meet with wholesale and retail suppliers to assess delivery, pricing and storage issues by Q3  Develop plan to match supply to increasing demand by Q4 Coordinate with local marketing efforts and cable television show to ensure timely availability of promoted produce |  Increase retail marketing of fresh produce through local suppliers and markets by 20% as measured in sales figures  Improve availability of fresh food items in ten neighborhood markets by 50% by 2012 |
| Media | Objective 3: Increase fruit and vegetable consumption and heart-healthy diet working through extensive community-wide media campaign |  CPPW Healthy Food/Dining Coordinator* and CPPW Media Coordinator* to work with CPPW Community Health Interpreters* to research, develop, design and market an outdoor advertising and radio and cable TV counter-advertising campaign to discourage the consumption of sugary drinks and high fat/calorie foods ("fast foods") in English, Portuguese, & Spanish  Identify high visibility locations for print media placement  Test market and evaluate effectiveness of pilot program; revise and re-market; evaluate effectiveness through community surveys |  Work with MA DPH staff to identify successful marketing strategies by Q3  Work with local print, outdoor and electronic media representatives to explore options and prices by Q4  Develop a marketing plan by Q5 to coordinate w/other local efforts; produce and test market products by Q6, release & evaluate in Q7 and Q8 |  Produce an effective marketing campaigns in three local languages on local radio and cable television to support reduced "fast food" & sugary drink consumption |
| Access Social Support | Objective 4: Increase the number of new mothers breastfeeding by providing teaching, social support and institutional and environments support |  CPPW Healthy Food/Dining Coordinator* and CPPW Community Health Interpreters* to work with Charlton Hospital maternity unit and WIC to assist in developing social support groups ("Baby Cafes") for breastfeeding mothers through the Mass. Breastfeeding Coalition  Work with local institutions and employers to encourage the development of worksite breastfeeding stations throughout the community |  Work with maternity and WIC staff to research issues pertinent to breastfeeding promotion and support in the community by Q3  Help to develop social support groups through local organizations by Q5  Work with employers to provide breastfeeding stations in at least 10 worksites |  Increase community-wide support for breastfeeding mothers through social, institutional and environment support and provision of breastfeeding stations at 10 worksite locations |
| Community Goal VI: Increase Use of Healthy Dining Guide and Guide to Meetings and Events |  |  |  |  |
| MAPPS Strategy: Promote healthy food/drink choices & increase availability; signage for healthy/less healthy food items; menu labeling |  |  |  |  |
| MAPPS Criteria | Objective | Key Activities | Timeline | Outcome |
| Access Point of Purchase | Objective 1: Increase the number of restaurants that participate in the Fall River Healthy Dining program by 200% |  CPPW Healthy Food/Dining Coordinator* to work with City food inspectors and licensing application process to identify and support additional restaurants to participate in city's Healthy Dining project  To research and add Healthy Children's menu criteria and promote through Healthy Dining restaurants  Work with City tourism director to integrate Healthy Dining program with tourism promotional materials  Apply Healthy Eating Index to evaluate menus |  Survey current 22 participating restaurants to review compliance with criteria/problem-solve by Q3  Market and expand participation by 100% through program promotion efforts by Q5  Coordinate marketing of program through City tourism office by Q7 |  Increase the number of Healthy Dining restaurants by 200% through a system of incentives, marketing and promotion  Integrate the system into area tourism Objectives |
| Media Point of Purchase | Objective 2: Ensure a wide community understanding of statewide calorie count labeling law to increase its use in food selection at local restaurants |  CPPW Healthy Food/Dining Coordinator and MA DPH to develop and coordinate local educational "Calories Count" media campaign in concert with new statewide calorie count labeling law in Nov. 2010  Test market, evaluate and launch program as part of city-wide Healthy Food campaign |  Work with MA DPH to understand and coordinate with planned statewide promotion efforts by Q2  Develop coordinated local media campaign by Q3  Launch, evaluate and support campaign through Q5  Evaluate & revise | Ensure community-wide understanding of calorie count labeling and ways of integrating information into healthier food choices at area restaurants |
| Access Point of Purchase Price | Objective 3: Encourage organizations to adopt Healthy Meeting/Event Guidelines; assist them with compliance; increase access to healthier food at a lower prices |  CPPW Healthy Food/Dining Coordinator* to promulgate the use of the Healthy Meeting and Events Guide among city organizations and worksites  Work with local food providers to increase the availability of healthier food items at a reasonable price by increasing volume of sales though local vendors  Provide training at worksites in menu selection and purchasing techniques; work with CPPW Media Coordinator* to integrate Guide with city-wide Healthy Food & Drink marketing campaign and promote through media |  Research availability of healthier food items through local providers by Q3  Develop listing of items and prices and publish to a minimum of 30 organizations by Q5  Work with providers to obtain healthier food items at lower prices by Q6  Monitor use of guidelines, revise approach and expand guideline use by 200% by Q7 |  At least 30 employers with more than 25 employees will participate in the selection and purchase of food that complies with the Guide to Healthy Meetings and Events by 2012  More affordable healthier food items will be made available by Q3 to Q7 among selected vendors |
| Access Media | Objective 4: Get the City Board of Health and Food Licensing Department to make promotion of the Healthy Dining program and adoption of Guidelines City policy |  CPPW Healthy Food/Dining Coordinator* will work with the Board of Health and the Office of Food Licensing to move to mandate the inclusion of Healthy Dining application materials with annual food sales license renewal process  Work with the Mayor and the City administrator to mandate the use of the Guide to Healthy Meetings and Events as policy  Work with City vendors to include Guide specifications for the purchase of food for City-sponsored meetings and events |  Work with Board of Health and Food Licensing Department to review current procedures by Q3  Prepare materials for distribution with 2011 food license applications by Q4  Monitor application process and report to BOH by Q5  Revise and renew program for 2012; work with City administrator on adoption of Guidelines by Q7 |  The Healthy Dining program application process will become part of the standard food licensing application process for area food providers by 2010  Guideline adoption by the City will occur by the end of 2011. |
| Access Social Support | Objective 5: Ensure make Healthy Dining list and Guide to Healthy Meetings and Events accessible to bilingual populations |  CPPW Community Health Interpreters* (2) to provide culturally-appropriate translation and interpretation of Healthy Dining restaurant list and Guide to Healthy Meetings and Events and other media campaign materials available to Portuguese- and Spanish-speaking populations  CPPW Media Coordinator* will include promotion of list and Guide in Healthy Food promotion campaign; monitor use of list and guide w/survey |  Work with identified and new Portuguese, Spanish and Khmer groups to identify access concerns by Q3  Provide translated materials by Q4 and throughout project period; Use social support channels to support use list & Guide among 20 non-English-speaking organizations |  At least 20 bilingual organizations will be supplied with and introduced to translations of Healthy Restaurant list and Guide to Healthy Meetings and Events |

† CPPW Community Action Plan Legend

| Acronyms and Initialisms | Expanded Description |
| --- | --- |
| ACHIEVE | Communities for Health Innovation and Environmental ChangE Action CDC grant |
| BOH | Fall River Board of Health |
| CIB | Children In Balance Tufts University research project |
| CDC | Centers for Disease Control and Prevention |
| CPPW | Communities Putting Prevention To Work |
| HEAT Club | CIB Healthy Eating Active Time Club |
| MassRides | Mass. DOT contractor for Safe-Routes-To-School |
| MA DPH | Massachusetts Department of Public Health |
| Q1, Q2, Q3, Q4 | Federal calendar quarters |
| SNAP EBT | USDA Supplemental Nutrition Assistance Program Electronic Benefit Transfer |
| SRPEDD | Southeastern Regional Planning & Economic Development District |
| SRTA | Southeast Regional Transit Authority |
| TTOR | The Trustees of Reservations, Managers of the Fall River Bioreserve |
| USDA | United States Department of Agriculture |
| WIC | USDA Women, Infants and Children Food & Nutrition |